## Project Portfolio Dash
PROJECT PORTFOLIO DASHBOARD TEMPLATE
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
PROJECT NAME | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A
Project B
Project C
Project D
Project E
Project F
Project G
Project H
Project J
Project K
Project L
Project M
Project N
Project P
DASHBOARD DATA
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Project A | 2025-05-01 | 2025-05-05 | 2025-07-01 | 57 | 10 | 1000000 | 880000 | 120000 | 1 | 0 | 4 | 2 | 0 | 4
Project B | 2025-06-01 | 2025-05-10 | 2025-08-10 | 92 | 5 | 900000 | 920000 | -20000 | 2 | 3 | 5 | 1 | 2 | 3
Project C | 2025-07-01 | 2025-06-10 | 2026-03-01 | 264 | 10 | 860000 | 850000 | 10000 | 3 | 4 | 3 | 2 | 1 | 2
Project D | 2025-08-01 | 2025-06-22 | 2025-08-04 | 43 | 5 | 1000000 | 998050 | 1950 | 5 | 8 | 1 | 1 | 0 | 0
Project E | 2025-09-01 | 2025-07-14 | 2025-11-01 | 110 | 10 | 294000 | 280000 | 14000 | 8 | 6 | 4 | 0 | 3 | 1
Project F | 2025-10-01 | 2025-07-14 | 2026-01-20 | 190 | 5 | 123400 | 125000 | -1600 | 5 | 0 | 0 | 2 | 0 | 2
Project G | 2025-11-01 | 2025-08-01 | 2025-10-01 | 61 | 10 | 250500 | 246000 | 4500 | 6 | 4 | 0 | 1 | 2 | 3
Project H | 2025-12-01 | 2025-08-14 | 2025-08-30 | 16 | 5 | 127200 | 126000 | 1200 | 7 | 3 | 3 | 0 | 1 | 4
Project J | 2026-01-01 | 2025-09-01 | 2025-12-10 | 100 | 10 | 80000 | 79900 | 100 | 0 | 2 | 4 | 1 | 3 | 2
Project K | 2026-02-01 | 2025-10-01 | 2025-11-15 | 45 | 5 | 77000 | 77000 | 0 | 4 | 4 | 5 | 2 | 0 | 0
Project L | 2026-03-01 | 2025-10-01 | 2025-12-01 | 61 | 10 | 65000 | 65000 | 0 | 3 | 6 | 4 | 3 | 2 | 0
Project M | 2026-04-01 | 2025-11-01 | 2025-12-01 | 30 | 5 | 550000 | 551000 | -1000 | 2 | 3 | 6 | 0 | 1 | 1
Project N | 2026-05-01 | 2025-11-10 | 2025-12-10 | 30 | 10 | 45000 | 42000 | 3000 | 1 | 1 | 7 | 1 | 0 | 2
Project P | 2026-06-01 | 2025-12-01 | 2026-02-10 | 71 | 5 | 32500 | 33000 | -500 | 5 | 0 | 2 | 2 | 1 | 3
[6 empty] | 5404600 | 5272950 | 131650 | 52 | 44 | 48 | 18 | 16 | 27
CLICK HERE TO CREATE IN SMARTSHEET

## Project Portfolio Dash - BLANK
PROJECT PORTFOLIO DASHBOARD TEMPLATE | [8 empty] | **Enter data in the table beginning on Row 38
DELIVERY TIMELINE & RESOURCES
PROJECT FINANCIALS
RISK ANALYSIS
OPEN & PENDING ACTIONS
PROJECT REPORT
PROJECT NAME | SCHEDULE | BUDGET | RESOURCES | RISKS | ISSUES | COMMENTS
Project A
Project B
Project C
Project D
Project E
Project F
Project G
Project H
Project J
Project K
Project L
Project M
Project N
Project P
DASHBOARD DATA
**Delete unused rows to correctly populate charts and graphs, above.
**User to complete non-shaded cells only.
PROJECT NAME | TIMELINE |  |  |  | NUMBER OF TEAM MEMBERS | BUDGET |  |  | RISKS |  |  | OPEN |  | PENDING ACTIONS
| CALENDAR | BEGIN | FINISH | # of DAYS |  | PROJECTED | ACTUAL | REMAINDER | HIGH | MEDIUM | LOW | ISSUES | REVISIONS
Project A |  |  |  | 0 |  |  |  | 0
Project B |  |  |  | 0 |  |  |  | 0
Project C |  |  |  | 0 |  |  |  | 0
Project D |  |  |  | 0 |  |  |  | 0
Project E |  |  |  | 0 |  |  |  | 0
Project F |  |  |  | 0 |  |  |  | 0
Project G |  |  |  | 0 |  |  |  | 0
Project H |  |  |  | 0 |  |  |  | 0
Project J |  |  |  | 0 |  |  |  | 0
Project K |  |  |  | 0 |  |  |  | 0
Project L |  |  |  | 0 |  |  |  | 0
Project M |  |  |  | 0 |  |  |  | 0
Project N |  |  |  | 0 |  |  |  | 0
Project P |  |  |  | 0 |  |  |  | 0
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your data table.*

## – Disclaimer –
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.